## sheet1
Week # | Date | Tasks and milestones | Assigned to | Completed by | Remarks
1 | 2022-02-11 | Group meeting | Kiran & Soumya | Kiran & Soumya
|  | Brainstorming ideas | Kiran & Soumya | Kiran & Soumya
2 | 2022-02-17 | Group meeting to finalize the idea | Kiran & Soumya | Kiran & Soumya
|  | - To Understand the scope of the ideas presented | Kiran & Soumya | Kiran & Soumya
|  | - Discussed on the datasets | Kiran & Soumya | Kiran & Soumya
|  | -Discussed on the sample projects presented | Kiran & Soumya | Kiran & Soumya
3 | 2022-02-21 | Data Mining | Kiran & Soumya | Kiran & Soumya
| 2022-02-23 | Data Cleaning | Kiran | Kiran
| 2022-02-23 | Statistical Analysis | Soumya | Soumya
| 2022-02-24 | Report creation | Kiran | Kiran
5 | 2022-03-03 | Group meeting | Kiran & Soumya | Kiran & Soumya
| 2022-03-05 | Data Mining for carfax | Kiran | Kiran | Due to robot ic process, we were not able to mine the data in thousands, we had to drop this project
6 | 2022-03-07 | Group meeting for selecting new project | Kiran & Soumya | Kiran & Soumya
7 | 2022-03-14 | - Understanding the newly selected project | Kiran & Soumya | Kiran & Soumya
7 | 2022-03-16 | Data collection & Data Cleaning | Kiran | Kiran
8 | 2022-03-24 | Analysis of the data | Soumya | Soumya
9 | 2022-03-25 | Modelling on the data | Kiran & Soumya | Kiran & Soumya
9 | 2022-03-30 | Report creation | Kiran & Soumya | Kiran
10 | 2022-04-04 | Discussed on next steps | Kiran & Soumya | Kiran & Soumya
10 | 2022-04-07 | Worked on next steps on model | Kiran | Kiran
11 | 2022-04-18 | Presentation slide | Soumya | Soumya
12 | 2022-04-28 | project report final | Kiran & Soumya | Kiran & Soumya